## Slide 1: Introduction to Project Management

## Slide 2: Objectives
To provide participants with:
  An awareness of the importance of applying good practice Project Management in projects of any size.
  An understanding of essential elements, including the Leadership Role of the Project Manager, Project Planning, Risk Management and Stakeholder Engagement.
  An understanding of the principle elements of design control to be applied within projects at Culham.

## Slide 3: Challenges
“What are the particular technical challenges facing projects?”
  Research environment
    requirements may be hard to define and may change
    producing one or a few items rather than production line
  Uncertainties of leading edge R&D 
    solutions may have to be developed, including possibly new technologies
    ‘first of a kind’ so planning and estimating is difficult
  Need to balance the desire to get maximum performance versus achieving acceptable reliability/availability

## Slide 4: Challenges
“What are the particular management challenges facing projects?”
  Requirements hard to define and may evolve
  Risk Management (all aspects) crucial but difficult
  Cross functional team composition
  Competing pressures on resources, e.g. design office
  Working with scientific organisations not used to project and QA disciplines  planning may be poor
  Collaborative agreements rather than contracts
  Political - EC funding requirements
  Growing funding pressures due to ITER

## Slide 5: What is a Project?
“Unique process consisting of a set of coordinated and controlled activities with start and finish dates, undertaken to achieve an objective conforming to specific requirements, including constraints of time, cost, quality and resources”
A Project is a planned set of activities
A Project has a scope
A Project has time, cost, quality and resource constraints

## Slide 6: What is Project Management?
The art of organizing, leading, reporting and completing a project through people

## Slide 7: What is Project Management?
A project is a planned undertaking
A project manager is a person who causes things to happen
Therefore, project management is causing a planned undertaking to happen.

## Slide 8: Feedback
What are three attributes of a good Project Manager

## Slide 9: Project Manager Role
A Good Project Manager
  Takes ownership of the whole project
  Is proactive not reactive
  Adequately plans the project
  Is Authoritative (NOT Authoritarian)
  Is Decisive
  Is a Good Communicator
  Manages by data and facts not uniformed optimism
  Leads by example
  Has sound Judgement
  Is a Motivator
  Is Diplomatic
  Can Delegate

## Slide 10: Stakeholder Engagement

## Slide 11: Stakeholder
“A person or group of people who have a vested interest in the success of an organization and the environment in which the organization operates”

## Slide 12: Feedback
What are three typical project stakeholders

## Slide 13: Feedback - Typical Stakeholders
Sponsor
Funding Body
Customer
Suppliers
End User
HSE/Environmental Agency
Maintenance Team
Neighbours/Community/Shareholders
Fusion Community
Interfaces

## Slide 14: Stakeholder Engagement process
Identify Stakeholders
Assess needs
Define actions
Establish communication channels
Gather feedback
Monitor and review

## Slide 15: The Project Process
Project set-up
Major Project Proposals
Project Definition
Conceptual Design
Scheme Design
Detailed Design
Tender Invitation & Assessment
Manufacture Equipment
Install Equipment
Confirm Completion
Test & Commission
Project Review
Appoint Project Sponsor Assess Project Priority Assess Budget Implications Est. Proj. Deliverables and Objectives Appoint Project Leader Approve Project Set-up
Draft Statement of Requirements (SoR) Review & Approve SoR Identify Resources Appoint Project Team Produce & Maintain Procurement Plans Undertake Project Risk Assessment Prepare Project Boundary Document Develop Project Management Plan (PMP)* Raise initial TCD-R/PERF** Prepare Preliminary Conceptual Design**
Raise/Extend/Update initial TCD-R/PERF Prepare Outline Conceptual Design Define Design Constraints Prepare Interface Requirements Spec. (IRP) Finalise Conceptual Design Hold Conceptual Design Review (CDR) Clear CDR Issues Initiate Modification Safety Case Update PMP Approve Proceed to Detailed Design
Raise/Extend Sub-system TCD-Rs/PERFs Agree Classifications & Interfaces Prepare Sub-system Scheme Design Hold Sub-system Scheme Design Review (SDR) Clear Sub-system SDR Issues Update PMP Use TCD-I/MMAC for Sub-system SD Approval
Extend TCD-Rs/PERFs Prepare Sub-system Detailed Design Hold Detailed Design Review (DDR) Clear Sub-system DDR Issues Use TCD-I/MMAC for Sub-system DD Approval Prepare Final Documents including: - Design Documents., Machine Compatibility Documents., Safety Case Modification
Compile Tender Docs.*** Send out Invitations (ITTS) Hold Clarification Meetings Receive Tenders Evaluate Tenders Arrange site visits Approve changes to Specs. Choose preferred Company
Raise Contract Documentation Place Contract Hold Kick off Meeting (KOM) Clarify Issues (Quality Plan) Monitor Progress Witness key Procedures Complete Release Note Approve Complete Package**** Approve Release Note Pack & Dispatch Equipment
Receive Equipment Pre-test Equipment Install equipment
Test Equipment against Test Schedule Commission Complete System
Confirm Technical Completion Review Project Records Complete Handover Documents Resolve Reservations Obtain Acceptance of Completed Project
Initiate Project
Undertake Design
Implement Project
Complete Project
EFDA/CSU/JOC Management
Project Leader/Project Team/EFDA/CSU
Project Team/IRP/EFDA/CSU/JDC
Project Team/Interfaces
Project Team/Interfaces/EFDA/CSU/JDC
Project Team/ICM
Project Team/ICM/EFDA/CSU
Project Team/EFDA/CSU
Project Team/CSU
Undertake Post Project Review
Project Team/Contracts/EFDA
Project Team/Contractor/ICM
Prepare Technical Design Ensure Machine Compatibility Prepare Safety Case Modification
*** These will comprise:
- Technical Specification - Drawings - Contractual Requirements
Note: Overall Project Management and Reporting will be as defined in the Project Management Plan (PMP)
**** This includes supporting documentation
Gate 4
Gate 1
Gate 2
Gate 3
Gates (Formal Decision Points) See accompanying notes
Gate 0
Project Justification - Approve Project Definition
Design Approval - Approval of Final Documents
Readiness for Manufacture - Approval to place Contract
Readiness for Operation - Acceptance of System
Strategic and Budgetary Approval
Undertake Tender
* This will include:
- Initial WBS, OBS and CBS - Project Plan - Risk and Procurement Strategies
** These will only take place here for large projects demanding DO effort for preliminary Conceptual work
UNCONTROLLED WHEN PRINTED

## Slide 16: Key Points in Project Set-up and Definition
Create Project Management Plan (PMP)
Be clear of scope and objectives
Establish clear statement of what is to be done (WBS)
Establish Risks to be Managed
Establish Costs and Durations
Establish Resources Required

## Slide 17: Project management Plan - PMP
Master Document for Project
Defines the following:-
  Project Objectives, Scope, Deliverables
  Stakeholders (Internal & External)
  Work to be done (WBS)
  Project Organisation and Resources (OBS)
  Project Costings (CBS)
  Project Schedule
  Procurement/Contract Strategy
  Risk Management
  Quality management
  Change Management

## Slide 18: Project Planning

## Slide 19: Project Planning
Adequate planning leads to the correct completion of work

## Slide 20: Planning
Inadequate planning leads to frustration towards the end of the project & poor project performance
Project Start
Project End

## Slide 21: Work Breakdown Structure (WBS)
The Work Breakdown Structure is the foundation for effective project planning, costing and management.
It is the most important aspect in setting-up a Project
It is the foundation on which everything else builds

## Slide 22: Work Breakdown Structure - Definition
“A Work Breakdown Structure (WBS) is a hierarchical (from general to specific) tree structure of deliverables and tasks that need to be performed to complete a project.”

## Slide 23: Example WBS - Top Level ILW Project

## Slide 24: Example WBS - Top Level TSCL Project

## Slide 25
Project Planning – WBS (1)
Lowest Level of WBS is the Work Package (WP)
WP can be clearly defined allowing package to be costed, scheduled and resourced
WP contains a list of Tasks to be Performed that form the basis for the Schedule
WP allows assignment of responsibilities (Work Package Manger, WPM)

## Slide 26
Project Planning – WBS (2)
WBS allows hierarchical build-up of costs and schedule
Cost and Schedule can be reported at any level of the WBS
WBS facilitates strong management during project execution (Cost and Schedule control)
WBS can be used for many other things - Document Management, Risk Management etc.

## Slide 27
Project Planning
A word about Scheduling
  Schedules (task durations) can have a wide variation
  There is no unique answer. Rather, there is a statistical variation depending on assumptions
  Need to understand the basis of scheduling (Most challenging; Most likely; Absolute certainty - bet your life on it!)
  Most people are very optimistic/naive

## Slide 28: Project Planning – Key Points
Recognise that adequate project planning is essential
Produce a sound WBS
Use the framework provided by the Project Management Plan (PMP) template
Involve the right people
Allow enough time
Be systematic

## Slide 29: Project Risk Management

## Slide 30: Project Risk – Definition (1)
“Project risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on a project objective”

## Slide 31: Project Risk – Definition (2)
“A combination of the probability of a defined threat or opportunity (Likelihood) and the magnitude of the consequences of the occurrence (Impact) defines a Risk Index”

## Slide 32: Risk Impact
Threat → Scope → Poor Quality Product
Threat → Schedule → Late Delivery
Threat → Cost → Overspend
In addition there are health, safety and environmental threats that must be managed (CDM Regulations)

## Slide 33: Risk Management Process
Identify Risks
Assess likelihood and impact
Rank risks and prioritise
Define risk management approach & actions
Implement actions
Monitor & review

## Slide 34: Risk Management – Key Points
Make the management of risk integral to the way the project is managed
Ensure that cost and time contingencies are consistent with identified risks
Focus on the “significant few” – don’t try to manage too many risks
Be vigilant and proactive

## Slide 35: Project Monitoring and Control

## Slide 36: Feedback
What are three typical project control/monitoring activities

## Slide 37: Project Monitoring
Typical Monitoring Activities
  regular reviews of progress against schedule using WBS as basis (Plan against Baseline)
  regular review of actual costs (O/P from SAP) against budgeted costs and Earned Value at WBS level
  regular review of resource loading
  regular progress meetings with project team
  regular meetings with contractors
  production of periodic progress reports
  risk reviews
  inspections/ audits

## Slide 38: Project Control
Typical Control Activities
  assign responsibilities at Work Package level
  staged authorisation of work to be done
  staged release of budgets (staged release of WBS(e) numbers)
  ensure PM has a ‘Management Reserve’ under his control
  seek corrective action reports when WPs go ‘off track’ (overrunning or overspending)
  release Management Reserve carefully

## Slide 39: Project Monitoring and Control Summary
Monitor against the plan – status regularly
Take a factual approach to decisions
Identify management action early
Check that defined controls are being applied – correct if necessary
Apply change control

## Slide 40: Design Management
Design takes place as part of a project
Design Management is part of Project Management
Design Management considerations must be included in the PMP

## Slide 41: Feedback
What are three Design Management Activities

## Slide 42: Feedback - Design Management Activities
Sub-divide Design Stages (CD, SD & DD)
Sub-divide Tasks (WBS)
Define Constraints and Interfaces (WPD Summary Sheet)
Formally Initiate the Design (TCD-R/PERF)
Ensure Design conforms to H&SE and CDM Requirements
Hold Design Reviews (Peer review)
Formally Approve Design (TCD-I/MMAC)

## Slide 43: Design Stages
Conceptual Design
Scheme Design
Detailed Design

## Slide 44: Conceptual Design Phase
TCD-R
Decide Local or TCS route
Develop Conceptual Design
Define Constraints & Interfaces
Carry out Conceptual Design Review
Initiate Safety Case Modification if required
Obtain Approval to Proceed to next stage

## Slide 45: Scheme and Detailed Design
Basic considerations and process similar to concept
Need to ensure that safety & environmental issues receive proper consideration as design develops (CDM Regulations)

## Slide 46: Feedback
Who should be invited to a design review
Write down three issues that should be considered at a design review

## Slide 47: Feedback - Design Reviews, Attendance
Project Leader or nominee (Chairman)
RO (Work Package Manager)
Customer
End User
Safety and Quality Reps
All other Relevant Interfaces/Stakeholders
Other Experts in the area being reviewed

## Slide 48: Feedback - Design Reviews, Issues to Consider
Assumptions and Constraints
Technical Solutions - Does it meet the Spec?
Safety, Environment and CDM issues
Can it be Manufactured/Maintained?
Actions from previous DRs
Issues to be resolved (including Timescales)

## Slide 49: Safety & Environment
Need to ensure that safety & environmental issues receive proper consideration as design develops
  Involve the right people from the start
  Systematically identify issues – Hazards/Risks, Environmental Aspects & Impacts
  Carry out rigorous reviews at each design stage
  Control Design Changes
MUST take note of CDM Regulations

## Slide 50: CDM Regulations
CDM - Construction (Design & Management)
Regulations recently updated
Now must have someone in EACH Project Responsible for CDM
Currently information is on the Conceptual, Scheme & Detailed Design steps on the Process Maps
More information will be developed over the coming months

## Slide 51: Design Change control
Needs to be a formal and defined procedure
New procedure in place CD/P/J008 for JET Facilities

## Slide 52: Confirm Completion
Ensure design records are complete and accurate
Ensure any outstanding actions or issues are addressed
Ensure Maintenance Records are produced
Ensure User Manuals are produced
Hold a formal Post Project review